## Sheet1
Week | Tasks | Allocated to |  | Group | Name
3 | Team formation | - |  | 1 | June, Wei Leng, Wesley
| Task allocation | - |  | 2 | Sri, Tiffany, Jia De
|  |  |  | 3 | Lim Guan, Xu Ai, Hong Jing
| SRS | 1,2,3
| Class diagram | 2 |  | Datelines
| ER diagram | 3 |  | 2003-09-01 | All diagram draft ready, meet at 4.30pm
| Sequence diagram | 1
| Use case diagram | 1
5 | Model system spec
Refine all diagrams and SRS
7 | Design prototype
Refine all diagrams and SRS
9 | Refine prototype
Refine all diagrams and SRS
11 | All should be done, ready for demo during lab
ALL FUNCTIONS
User | Create survey | System | Logging of surveys and data
Create survey questions
| Create survey options | Respondents | Submit Survey
Update survey
| View survey | Side notes | Question can have different types (include slider has bonus marks)
| Close survey |  | User can customize survey page (maybe)
| Generate survey report |  | Set time boundaries for survey
| View survey report |  | Shorter link (maybe)
| Export survey results |  | Take photo upload to storage
| Login |  | Signature from respondent
| Create user account |  | Date time picker
| Update user account |  | Forget password
| View user account |  | Visualization graph data report